## InProcess_ToDo_List
Functionality | Functionality brief | CRM/Magento/URL/ Telephony/Training/Functional | Task Status | Priority | Remarks
Lead generation | Lead generation through incoming call | CRM | To do | Very High | In progress | Now
Lead generation | Lead generation through email | CRM | To do | High
Name display | Name display, of lead/customer, in case record already exists | CRM | To do | Very High | Done
Screen pruning | To delete unwanted functionalities from CRM screen | CRM | To do | Very High | Done
Multiple address | Options to store multiple customer addresses | CRM | in process | Very high | Done on CRM pending on Magento
Multiple address | Addresses that are added in Magento, should get picked in CRM | CRM | In process | Very high | Done on CRM pending on Magento
Validation | Every time primary emal id & mobile number is changed in CRM, same must get updated in Magento | CRM | In process | High | Hold
Master list - City, State | Drop down option for State and City | CRM | In process | High | Hold
API Token | Fix token in API's | CRM | To do | High | Hold
Defect - Call logs | Call logs to be frozen (make non-editable), once made | CRM | To do | Very high | For Testing
Defect - Minute information | Reminders to have have minute level information | CRM | To do | Very high | In progress | Now | Azad
Defect - Date fromat | All screens to have same date format i.e. DD/MM/YYYY | CRM | To do | Very high | Done from our end if left anywhere let us know the screen
Defect - Call log (Lead & customer page) | Subject field should take only alphabet?? | CRM | To do | Very high | Not needed
GitHub setup | Setup Github |  |  |  | Will do once the things get completed.
Code testing | Selenium testing |  |  |  | Will be our next phase when our development & bug fixing is completed
CRM training
List of Masters | List of Masters used across platform |  |  |  | Need to act
Explore Complaint module | Complaint module in CRM |  |  |  | Separate module
Explore Task Module | Task module in CRM |  |  |  | Separate module in CRM
Change status - forcing | Force Gyde expert to change lead/customer/call status